## Hoja1
			Time Sheet					Estimation
Total Expected Worktime	39:00		Date	Weekday	Workday	Expected Work time	Real Work Time	Advancement		Activity	Estimate	Advanced
Risk (Less time)	10%		Dec 22	TU	yes	01:00	2:00	3:00		$ Title Screen	1:00	01:00
Plan Time	35:06		Dec 23	WE	yes	00:00	0:10	1:00		* Mock Starmap generator	0:30	00:30
			Dec 24	TH	no	04:00	1:30	2:00		* Mock expedition generator	0:30	00:30
Total Estimate	50:00		Dec 25	FR	no	00:00	0:00	0:00		$ Starmap Navigation Screen	2:00	02:00
Risk (Underestimation)	15%		Dec 26	SA	no	04:00	3:30	4:30		* Mock sector generator	0:30	00:30
Covered Estimate	57:30		Dec 27	SU	no	04:00	3:30	5:30		* Mock assault group generator (3 Ships alone)	0:30	00:30
			Dec 28	MO	yes	01:00	3:30	3:00		$ Sector Navigation Screen	3:00	03:00
Plan Difference	22:24		Dec 29	TU	yes	01:00	0			# Sample Ship Data	0:30	00:30
			Dec 30	WE	yes	00:00	0			* Mock combat scenario generator (Alone)	1:00	01:00
Current EV	22:45		Dec 31	TH	no	04:00	0			$ Combat Screen / Queuing System	3:00	03:00
Current Difference	23:39		Jan 1	FR	no	00:00	02:00:00			> Fire Action (Ship)	2:00	02:00
			Jan 2	SA	no	04:00	01:15:00			> Thrust Action (Ship)	1:00	01:00
			Jan 3	SU	no	04:00	01:50:00			> Turn Action (Ship)	1:00	01:00
			Jan 4	MO	yes	01:00	01:00:00			> Brake Action (Ship)	0:30	00:30
			Jan 5	TU	yes	01:00	0			* Mock combat scenario generator (with enemy ships)	1:00	01:00
			Jan 6	WE	yes	01:00	0			* Simple Enemy AI	2:00	02:00
			Jan 7	TH	yes	1:00				# Sample SpriteGear Data	1:00	01:00
			Jan 8	FR	yes	0:00				* Mock combat scenario generator (with SpriteGear)	0:30	00:30
			Jan 9	SA	no	4:00				> Capture SpriteGear	1:30	01:30
			Jan 10	SU	no	4:00				* Mock assault group generator (2 Ships alone + 1 SpriteGear)	1:00	01:00
				# Intermediate Ship Data	1:00
				# Intermediate SpriteGear Data	1:00
				* Starmap generator	2:00	02:00
				$ Create Expedition	1:00
				* Expedition generator	1:00
				* Sector Generator	2:00	02:00
				$ Setup Assault Group	3:00	01:00

				* Missile and laser fire animation
				* SpriteGearAI, can summon slave ships
				* Add alien factions
				* Fighting over planets and asteroid fields
				* Add recovery to ships
				* SpriteGear capture
				* Tie battlescenario generator to section type and zone difficulty
				* Movement animations
				* Add flavour messages with portraits
				* Add expedition status screen
				* Add energy cost to ship warps
				* Add fancy ship warp animation
				* Add fancy starfield simulation parametrized by zone
				* Add mothership section tile to zone
				* Add friendly space station section tile to zone
				* Buy and sell ships and supplies at friendly space stations
				* Add quest sections, can do quests for energy to warp to other zones
				* Add a tutorial
				* Add pre battle setup (show what’s the enemy, then select a formation) [Stand Fast, Balanced Wedge, Line, Outflank, Inverse Edge] Each formation has an energy cost
				* SpriteGears have special moves which van be triggered via command, or used automatically while on crisis
				* SpriteGear are commonly weak at short range and need to be escorted
				* Show detailed ship data in a square on hover, including faction, model, direction, energy and an image.